## ResourceLoading
T-shirt Sizing to Hours
Size | Hours (editable)
XS | 2
S | 4
M | 8
L | 16
XL | 24
Effort Allocation |  | Ratio (editable)
Dev Hours
QA Hours |  | 0.4
PM Hours |  | 0.15
Architect Hours |  | 0.1
Buffer Hours |  | 0.2
Hours per Resource Day | 8
Resource Utilization
Role | Hours | Resource Days
Dev
QA
PM
Architect
Buffer

## Feature Input
Module Name | Feature Input
Module Description | Interface to input feature details for sizing
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Provide single text input field for feature description | XS | —
Include form fields to specify feature category and complexity | S | —
Validate mandatory fields before submission | S | —
Support multiline text input for detailed descriptions | XS | —
Show submission progress indicator | XS | —
Display error messages for invalid inputs | S | —
Enable editing of feature input before final submission | M | —
Persist draft feature inputs locally | M | —
Screens
Screen Title | Description
Feature Description | Input screen for feature text description
Feature Details Form | Form to add feature context and specifics
Feature Validation | Review and validate entered feature data
Submission Confirmation | Confirm successful submission of feature
Module Summary: | Allows users to submit detailed feature descriptions for sizing estimation
Screens: | 4
Total Module Hours (calculated):

## Sizing Engine
Module Name | Sizing Engine
Module Description | Core logic to estimate feature size based on input data
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Parse feature description text to identify keywords | M | —
Map identified keywords to predefined size estimations | M | —
Calculate overall feature size by summing requirement sizes | S | —
Present sizing results clearly and concisely | S | —
Allow manual override and adjustment of sizing values | M | —
Store sizing results with timestamp and user data | S | —
Enable retrieval and display of past sizing entries | M | —
Support export of sizing report as JSON or PDF | L | —
Screens
Screen Title | Description
Sizing Summary | Displays estimated sizing for input feature
Sizing Details | Breakdown of size by module and requirement
Adjustment Interface | Allows manual adjustment to sizing estimates
Sizing History | Lists previous sized features and estimates
Module Summary: | Processes feature input and outputs estimated effort sizing in hours
Screens: | 4
Total Module Hours (calculated):

## User Management
Module Name | User Management
Module Description | Manage user authentication and roles
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Implement secure login with password encryption | M | —
Support role-based access control for features | M | —
Allow users to view and update their profile details | S | —
Log all user actions for audit purposes | M | —
Enable admin role to create and delete user accounts | M | —
Timeout session after inactivity for security | S | —
Provide password reset functionality | S | —
Multi-factor authentication support | L | —
Screens
Screen Title | Description
Login | User authentication screen
User Profile | Display and edit user information
Role Management | Assign and modify user roles and permissions
Activity Log | Audit trail of user actions
Module Summary: | Controls access and tracks user activity related to feature sizing
Screens: | 4
Total Module Hours (calculated):

## Reporting & Analytics
Module Name | Reporting & Analytics
Module Description | Provide insights on sizing trends and usage
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Aggregate sizing data to calculate averages and medians | M | —
Generate charts for time-based trend analysis | L | —
Filter reports by date range and user | M | —
Allow export of reports in CSV and PDF formats | M | —
Display key insights and anomalies in dashboard | M | —
Support scheduled email reports delivery | L | —
Implement role-based report access | S | —
Provide drill-down capability from summary to detail data | L | —
Screens
Screen Title | Description
Dashboard Overview | Summary of overall sizing statistics
Trend Analysis | Visualization of sizing trends over time
User Activity Report | Reports on individual user sizing activities
Export Data | Export reports and data sets for external use
Module Summary: | Generates reports and analytics dashboards for feature sizing data
Screens: | 4
Total Module Hours (calculated):