## ResourceLoading
T-shirt Sizing to Hours
Size | Hours (editable)
XS | 2
S | 4
M | 8
L | 16
XL | 24
Effort Allocation |  | Ratio (editable)
Dev Hours | 232 | Static Dev Hours | 232
QA Hours | 92.8 | 0.4
PM Hours | 34.8 | 0.15
Architect Hours | 23.2 | 0.1
Buffer Hours | 46.4 | 0.2
Hours per Resource Day | 6
Resource Utilization
Role | Hours | Resource Days
Dev | 232 | 38.6667
QA | 92.8 | 15.4667
PM | 34.8 | 5.8
Architect | 23.2 | 3.8667
Buffer | 46.4 | 7.7333

## User Registration and Authentic
Module Name | User Registration and Authentication
Module Description | Handles creating and managing user accounts for students, teachers, and admins.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Implement role-based registration flow for Students, Teachers, Admins. | M | —
Validate unique email addresses for account creation. | S | —
Integrate secure password hashing and storage. | M | —
Develop login form with error handling for invalid credentials. | S | —
Enable email-based password reset workflow. | M | —
Include CAPTCHA protection on registration to prevent bot signup. | S | —
Allow users to update their profile information securely. | S | —
Implement session management with timeout support. | M | —
Screens
Screen Title | Description
Registration Screen | Users can sign up with role selection and input required details.
Login Screen | Users enter credentials to access the system.
Password Reset Screen | Users can request password reset via email.
Profile Management Screen | Users update personal information and preferences.
Module Summary: | Allows users to register, log in, reset password, and manage profile settings.
Screens: | 4
Total Module Hours (calculated): | 48 | Static total (Python) | 48

## Class and Schedule Management
Module Name | Class and Schedule Management
Module Description | Manage classes, timetables, and enrollment of students and teachers.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Allow admins to create and define classes with attributes. | M | —
Support scheduling class sessions with dates and times. | M | —
Enable student enrollment management per class. | M | —
Allow teacher assignment with role validation. | S | —
Provide calendar view for class schedules. | L | —
Prevent scheduling conflicts for students and teachers. | L | —
Include search and filter functionality for classes. | S | —
Send notifications to enrolled students and assigned teachers on schedule changes. | M | —
Screens
Screen Title | Description
Class List Screen | Displays all classes with details and status.
Create/Edit Class Screen | Forms to add or modify class information and schedules.
Student Enrollment Screen | Manage student registration to classes.
Teacher Assignment Screen | Assign teachers to classes and view assignments.
Module Summary: | Create, edit, and view class schedules and assign participants.
Screens: | 4
Total Module Hours (calculated): | 72 | Static total (Python) | 72

## Assignments and Grades
Module Name | Assignments and Grades
Module Description | Manage assignment creation, submission tracking, and grade recording.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Enable teachers to create assignments linked to classes. | M | —
Allow file uploads for student assignment submissions. | M | —
Track submission deadlines and late submissions. | M | —
Permit teachers to enter and edit grades per assignment. | S | —
Provide students visibility into submitted assignments and grades. | S | —
Send notifications to students on assignment creation and grading. | S | —
Support multiple file formats for submissions. | S | —
Allow teachers to leave textual feedback with grades. | S | —
Screens
Screen Title | Description
Assignment List Screen | Shows assignments per class with deadlines and status.
Create/Edit Assignment Screen | Form for teachers to define assignment details.
Student Submission Screen | Students upload assignments and track status.
Grade Entry Screen | Teachers record grades and provide feedback.
Module Summary: | Teachers create assignments and enter grades; students submit work.
Screens: | 4
Total Module Hours (calculated): | 44 | Static total (Python) | 44

## Notifications and Communication
Module Name | Notifications and Communication
Module Description | Facilitate communication between users via messages and system alerts.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Implement system notifications for assignment and schedule updates. | M | —
Enable direct user-to-user messaging with read receipts. | L | —
Allow users to filter and mark notifications as read or unread. | S | —
Support notification preferences per user. | S | —
Send email alerts for critical notifications. | M | —
Provide real-time message updates via web sockets or polling. | L | —
Store message history with secure access controls. | M | —
Allow attachment support in messages. | S | —
Screens
Screen Title | Description
Notification Center Screen | Centralized view for all system notifications.
Messaging Inbox Screen | Users view and send messages to others.
Compose Message Screen | Form to write and send new messages.
Notification Settings Screen | Users configure their notification preferences.
Module Summary: | Send alerts, reminders, and support message exchange in app.
Screens: | 4
Total Module Hours (calculated): | 68 | Static total (Python) | 68