## ResourceLoading
T-shirt Sizing to Hours
Size | Hours
XS | 1
S | 4
M | 8
L | 16
XL | 32
Total Development Hours | 260
QA Hours (40%) | 104
PM Hours (15%) | 39
Architect Hours (10%) | 26
Buffer (20%) | 52
Resource Utilization
Role | Hours | Resource Days (8h/day)
Dev | 260 | 32.5
QA | 104 | 13
PM | 39 | 4.875
Architect | 26 | 3.25
Buffer | 52 | 6.5

## Real-time Sales Data Collection
Module Name | Real-time Sales Data Collection
Module Description | Collect sales data from all retail store locations in real-time.
Number of Screens | 1
Requirement | Size (XS/S/M/L/XL) | Notes
Implement connectors to POS systems across stores | L | Needs support for various POS vendors
Real-time data ingestion pipeline | M | Ensure minimal latency
Error handling and retry logic for data feeds | M | Robustness is key
Data normalization and quality checks | M | Consistent format required
Scalability to handle large store chains | L | Performance under load
Secure data transmission and storage | S | —
Module Summary: | Connect and synchronize data feeds from multiple stores into a central repository.
Screens: | 1
Total Module Hours (calculated): | 60

## Demand Forecasting Engine
Module Name | Demand Forecasting Engine
Module Description | Analyze data and predict SKU-level inventory demand for coming periods.
Number of Screens | 1
Requirement | Size (XS/S/M/L/XL) | Notes
Develop algorithms for seasonality and trend analysis | L | Advanced ML/stat models
Incorporate promotional activity impact in forecasting | M | Dynamic adjustments
Generate forecasts for 30, 60, 90-day horizons | M | Multiple forecast views
SKU-level granularity support | M | High dimensional data handling
Model training and periodic retraining | L | Automated model updates
API to expose forecast data | S | —
Module Summary: | Leverage historical, promotional, seasonal, and pattern analysis for forecasting.
Screens: | 1
Total Module Hours (calculated): | 60

## Automated Replenishment Order G
Module Name | Automated Replenishment Order Generation
Module Description | Generate purchase orders based on forecast and stock data.
Number of Screens | 1
Requirement | Size (XS/S/M/L/XL) | Notes
Compare forecasts with current inventory levels | M | Accurate stock sync needed
Generate replenishment quantities automatically | M | Business rules applied
Allow manual override by store managers | S | User input integration
Priority management for urgent reorder | M | Stock-out risk mitigation
Audit trail for replenishment order changes | S | —
Module Summary: | Create suggested replenishment actions minimizing stock-outs and overstocks.
Screens: | 1
Total Module Hours (calculated): | 32

## Alerts and Notifications
Module Name | Alerts and Notifications
Module Description | Provide alerts for stock issues and unusual sales events.
Number of Screens | 2
Requirement | Size (XS/S/M/L/XL) | Notes
Detect potential stock-outs and overstock conditions | M | Threshold based alerts
Detect unusual sales spikes | M | Anomaly detection algorithms
Configure alert preferences per user/store | S | Personalization
Push alerts via dashboard and email | S | —
Alert history and logging | S | —
Module Summary: | Notify users on critical inventory events to enable timely actions.
Screens: | 2
Total Module Hours (calculated): | 28

## Store Manager Dashboard
Module Name | Store Manager Dashboard
Module Description | Dashboard for review, approval, and modification of replenishment suggestions.
Number of Screens | 3
Requirement | Size (XS/S/M/L/XL) | Notes
Display forecast and replenishment recommendations | M | Clear and intuitive UI
Enable approve/modify/reject actions on suggested orders | M | User workflow
Visualization of inventory trends and alerts | M | Graphs and key metrics
User authentication and role-based access control | S | —
Export reports for inventory and orders | S | —
Module Summary: | Provide an interactive UI for inventory decision-making and order management.
Screens: | 3
Total Module Hours (calculated): | 32

## Supplier Integration
Module Name | Supplier Integration
Module Description | Interface with supplier systems for order sharing and status tracking.
Number of Screens | 1
Requirement | Size (XS/S/M/L/XL) | Notes
Support common supplier EDI/API protocols | L | Multiple integration types
Send purchase orders electronically | M | Order generation and transmission
Receive and process order acknowledgments | M | Two-way sync
Track dispatch and expected delivery dates | M | Update inventory accordingly
Error handling and retry for failed transmissions | M | —
Module Summary: | Automate communication with suppliers for purchase orders and delivery updates.
Screens: | 1
Total Module Hours (calculated): | 48