## ResourceLoading
T-shirt Sizing to Hours
Size | Hours (editable)
XS | 2
S | 4
M | 8
L | 16
XL | 24
Effort Allocation |  | Ratio (editable)
Dev Hours | 224
QA Hours | 89.6 | 0.4
PM Hours | 33.6 | 0.15
Architect Hours | 22.4 | 0.1
Buffer Hours | 44.8 | 0.2
Hours per Resource Day | 8
Resource Utilization
Role | Hours | Resource Days
Dev | 224 | 28
QA | 89.6 | 11.2
PM | 33.6 | 4.2
Architect | 22.4 | 2.8
Buffer | 44.8 | 5.6

## Data Collection & Integration
Module Name | Data Collection & Integration
Module Description | Gather real-time sales and inventory data from all retail store locations.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Connect to POS systems at each store to fetch live sales transactions | L | —
Integrate with inventory management systems for current stock levels | L | —
Implement data normalization and cleaning processes | M | —
Store and update sales and stock data with timestamp metadata | M | —
Provide error reporting for failed or incomplete data ingestion | S | —
Create real-time dashboard for monitoring data feed health | M | —
Build API connectors for supplier system order exchanges | L | —
Screens
Screen Title | Description
Data Source Setup | Configure and monitor data feeds from store POS and inventory systems.
Real-time Data Dashboard | Visualize incoming sales and inventory updates across all locations.
Data Health Monitor | Display data integrity, latency, and errors from connected sources.
Integration Status | Show connection status and error logs for external supplier and store system APIs.
Module Summary: | Collect and aggregate sales and stock data continuously for forecasting.
Screens: | 4
Total Module Hours (calculated): | 76

## Forecasting Engine
Module Name | Forecasting Engine
Module Description | Analyze historical and real-time data to predict inventory demand.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Build algorithms to analyze sales patterns, seasonality, and promotions | XL | —
Generate demand forecasts at SKU and store level for 30, 60, 90 days | L | —
Detect and flag unusual sales spikes and anomalies | M | —
Provide visualization of trends and forecast outputs | M | —
Allow configurable forecasting time windows | S | —
Implement model retraining with updated data regularly | L | —
Support manual override and adjustments to forecast results | M | —
Screens
Screen Title | Description
Forecast Summary | Overview of forecasted inventory needs for 30, 60, and 90 days.
SKU Trend Analysis | Visualize purchase patterns, seasonal effects, and promotions impact.
Exception Alerts | Highlight unusual sales spikes or demand anomalies.
Forecast Configuration | Allow parameter adjustments for forecasting models and time horizons.
Module Summary: | Generate SKU-level demand forecasts for future periods using advanced analytics.
Screens: | 4
Total Module Hours (calculated): | 84

## Replenishment Order Management
Module Name | Replenishment Order Management
Module Description | Automatically generate and manage reorder quantities and purchase orders.
Number of Screens | 5
Requirement | Size (XS/S/M/L/XL) | Notes
Automatically generate replenishment orders based on forecast and stock levels | L | —
Send alerts for potential stock-outs and overstock conditions | M | —
Enable store managers to review, approve, or modify orders | M | —
Integrate with supplier systems for order submission and acknowledgment | L | —
Track order dispatch and expected delivery dates | M | —
Provide notifications for order changes and delivery status | S | —
Maintain audit logs of order approvals and modifications | S | —
Screens
Screen Title | Description
Replenishment Dashboard | Review suggested orders, inventory status, and alerts.
Order Approval | Interface for store managers to approve or adjust orders.
Order Tracking | Track purchase orders and delivery status from suppliers.
Alerts & Notifications | Notify managers of stock-outs, overstocks, and spikes.
Supplier Integration Status | Show connectivity and acknowledgment states with suppliers.
Module Summary: | Create and track replenishment orders based on forecasts and current inventory.
Screens: | 5
Total Module Hours (calculated): | 64