## ResourceLoading
T-shirt Sizing to Hours
Size | Hours (editable)
XS | 2
S | 4
M | 8
L | 16
XL | 24
Effort Allocation |  | Ratio (editable)
Dev Hours | 258
QA Hours | 103.2 | 0.4
PM Hours | 38.7 | 0.15
Architect Hours | 25.8 | 0.1
Buffer Hours | 51.6 | 0.2
Hours per Resource Day | 6
Resource Utilization
Role | Hours | Resource Days
Dev | 258 | 43
QA | 103.2 | 17.2
PM | 38.7 | 6.45
Architect | 25.8 | 4.3
Buffer | 51.6 | 8.6

## Inventory Management
Module Name | Inventory Management
Module Description | Manage kitchen ingredients and supply stock levels.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Add new ingredient to inventory | S | —
Edit ingredient details including quantity and expiry | M | —
Delete obsolete ingredients from inventory | S | —
View current stock levels in dashboard | S | —
Set reorder threshold per ingredient | M | —
Receive alerts when stock goes below threshold | M | —
Manage supplier profiles with contacts and notes | M | —
Link ingredients to suppliers | M | —
Generate purchase order suggestions based on low stock | L | —
Export inventory reports to CSV | S | —
Screens
Screen Title | Description
Inventory Dashboard | Overview of current stock levels and alerts.
Ingredient List | Detailed list of all ingredients with quantities and expiry.
Supplier Management | Manage supplier contacts and purchase history.
Stock Alert Settings | Configure threshold alerts for low stock.
Module Summary: | Tracks all ingredients, stock levels, suppliers, and alerts for replenishment.
Screens: | 4
Total Module Hours (calculated): | 72

## Recipe and Menu Management
Module Name | Recipe and Menu Management
Module Description | Create and manage recipes and link them with inventory usage.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Create new recipes with ingredient quantities | M | —
Edit existing recipes and instructions | M | —
Delete outdated recipes | S | —
Search recipes by name or ingredient | S | —
Build daily or weekly menus from selected recipes | M | —
Calculate total ingredient needs from menus | L | —
View recipe impact on inventory stock | M | —
Import/export recipe data | S | —
Tag recipes by category or dietary restrictions | S | —
Screens
Screen Title | Description
Recipe List | View and search all kitchen recipes.
Recipe Details | Create or edit detailed recipe steps and ingredients.
Menu Builder | Assemble daily or weekly menus from recipes.
Recipe Inventory Impact | View ingredient usage and stock impacts per recipe.
Module Summary: | Organizes recipes, calculates ingredient requirements, and builds menus dynamically.
Screens: | 4
Total Module Hours (calculated): | 64

## Order and Waste Tracking
Module Name | Order and Waste Tracking
Module Description | Track ingredient orders and record kitchen waste to optimize usage.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Create and send purchase orders to suppliers | L | —
Update order statuses (pending, received, cancelled) | M | —
View detailed order history with filters | M | —
Record waste incidents with ingredient and quantity | M | —
Categorize waste reasons (spoilage, overprep, etc.) | S | —
Generate waste reports by ingredient and time period | L | —
Export waste logs for audit purposes | S | —
Receive alerts for unusual waste patterns | M | —
Screens
Screen Title | Description
Order Management | Place and review orders with suppliers.
Order History | View past orders and statuses.
Waste Log | Record and categorize wasted ingredients.
Waste Reports | Analyze waste trends and identify optimization opportunities.
Module Summary: | Manages purchase orders, order history and documents food wastage for reporting.
Screens: | 4
Total Module Hours (calculated): | 72

## User and Role Management
Module Name | User and Role Management
Module Description | Control access and permissions for kitchen staff and suppliers.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Add new users with role assignments | S | —
Edit user details and reset passwords | S | —
Deactivate/reactivate user accounts | S | —
Create and edit user roles with granular permissions | M | —
Assign roles to users | S | —
Track and display user login and activity logs | M | —
Enforce password complexity rules | XS | —
Support multi-factor authentication setup | L | —
Screens
Screen Title | Description
User List | View and manage all system users.
Role Definition | Create and assign user roles and permissions.
Access Logs | Monitor user access and activity.
User Profile | View and edit individual user details and settings.
Module Summary: | Manages users, roles and authorizations to ensure secure and proper access.
Screens: | 4
Total Module Hours (calculated): | 50