## ResourceLoading
T-shirt Sizing to Hours
Size | Hours (editable)
XS | 2
S | 4
M | 8
L | 16
XL | 24
Effort Allocation |  | Ratio (editable)
Dev Hours
QA Hours |  | 0.4
PM Hours |  | 0.15
Architect Hours |  | 0.1
Buffer Hours |  | 0.2
Hours per Resource Day | 8
Resource Utilization
Role | Hours | Resource Days
Dev
QA
PM
Architect
Buffer

## Inventory Management
Module Name | Inventory Management
Module Description | Manage kitchen inventory including ingredients and supplies.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Track ingredient quantities with real-time updates | L | —
Alert user when stock level falls below reorder threshold | M | —
Allow adding and editing of inventory items | S | —
Maintain supplier contact information linked to items | M | —
Generate daily and monthly inventory usage reports | L | —
Support multiple units of measurement per item | M | —
Provide search and filter capability for inventory items | S | —
Screens
Screen Title | Description
Inventory Dashboard | Overview of current stock levels and alerts.
Add/Edit Inventory Item | Form for adding or updating inventory items.
Supplier Management | Manage supplier details and contact information.
Inventory Reports | Generate reports on inventory usage and trends.
Module Summary: | Tracks stock levels, alerts on low inventory, and manages suppliers.
Screens: | 4
Total Module Hours (calculated):

## Recipe Management
Module Name | Recipe Management
Module Description | Create and organize kitchen recipes linked to inventory items.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Create new recipes with ingredient linking to inventory | M | —
Edit and update existing recipe ingredients and steps | M | —
Calculate estimated recipe cost from inventory prices | L | —
Support portion scaling for different serving sizes | M | —
Allow tagging and categorization of recipes | S | —
Provide searchable and filterable recipe list | S | —
Display recipe instructions with images if available | M | —
Screens
Screen Title | Description
Recipe List | View and search existing recipes.
Add/Edit Recipe | Form to create or modify recipe details and ingredients.
Recipe Detail | Display detailed instructions and ingredient list.
Recipe Cost Analysis | Calculate cost based on current inventory prices.
Module Summary: | Manage recipes with ingredients, portions, and preparation instructions.
Screens: | 4
Total Module Hours (calculated):

## Order and Menu Planning
Module Name | Order and Menu Planning
Module Description | Organize daily menu plans and manage order requirements.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Create menu plans with assigned recipes by date | M | —
Generate ingredient quantity forecasts from menu plans | L | —
Create purchase orders to suppliers with order details | L | —
Track purchase order status and delivery confirmations | M | —
Allow editing and updating of existing menu plans | S | —
Provide overview/dashboard of upcoming menus and orders | M | —
Support exporting orders in common formats (PDF, CSV) | S | —
Screens
Screen Title | Description
Menu Planner | Create and edit menus for specific dates.
Order Forecast | Forecast ingredient needs based on planned menus.
Purchase Orders | Generate and track orders sent to suppliers.
Order History | View past purchase orders and statuses.
Module Summary: | Plan menus and generate ingredient orders based on demand forecasts.
Screens: | 4
Total Module Hours (calculated):

## User and Role Management
Module Name | User and Role Management
Module Description | Manage users, roles, and permissions for system access.
Number of Screens | 4
Requirement | Size (XS/S/M/L/XL) | Notes
Create and delete user accounts | S | —
Define roles with granular permissions | M | —
Assign roles to users for access control | S | —
Implement login authentication and session management | L | —
Track and display user activity logs | M | —
Support password reset and recovery mechanisms | M | —
Provide admin dashboard for user and role overview | S | —
Screens
Screen Title | Description
User List | View and manage system users.
Role Management | Create and assign roles with specific permissions.
User Detail | Edit user information and role assignments.
Activity Logs | Monitor user actions and system changes.
Module Summary: | Define access controls and track user activity in the system.
Screens: | 4
Total Module Hours (calculated):